## Sprint
Sprint 1
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Discussion on Problem Statement and Objectives | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
Research on project topics | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 10
Discussions on project topics | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 4 | 0 | 0 | 10
Create Solution Design Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 10
Total Effort | 40
Actual Effort | 56
Effort Remaining | -16
Sprint 2
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Create & Finalise Database Design | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Create & Finalise Api Design | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8
Create & Finalise Wireframes Design | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 8
HTML CSS Design | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 8
Documentation & Scrum | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 6
Solution Design Presentation Slides | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 2 | 8
Finalise Initial Report | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 2 | 6
Total Effort | 52
Actual Effort | 71
Effort Remaining | -19
Sprint 3
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Solution Design Presentation | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Story(database): As a developer, I want to set up a mongodb database so that I can persist the necessary data. | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 5
Story(database): As a developer, I want to define the product schema so that I will know what is the necessary info and use it to design the front end and backend. | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 4
Story(database): As a developer, I want to define the user schema so that I will know what is the necessary info and use it to design the front end and backend. | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 4
Story(database): As a developer, I want validation for the collection schemas so that the chances of bad data in the database is minimised. | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 5
Story(database): As a admin user, I want to define product type schema so that users can only create products with a predefined set of product types. | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 4
Story(user-management) As an employee, I want to be able to create an account so that I can create and update the products. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 7
Story(user-management) As the site owner, I want registered users to be able to create, view and edit products so that authorised personnel are able to make changes to the database. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 7
Story(user-management) As an admin, I want users in normal user role to only be able edit their own products so that unauthorised edits are not made. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 4
Story(user-management) As an site-owner, I want users in admin role to be able to delete users so that inactive users can be purged from the system. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 0 | 8
Story(user-management) As an site-owner, I want a user in admin role to be able edit and delete other users products so that I can correct mistakes. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 8
Story(user-management) As an admin, I want users who are not logged in to only be able to view product cards and not edit them so that anonymous people can not modify data. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 8
Story(user-management): As a site owner, I want all users to be able to view products page, about page, home page and contact page | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 6
Total Effort | 73
Actual Effort | 83
Effort Remaining | -10
Sprint 4
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Story(user-management): As a site owner, I want only authorized users to be able to create an account so that I can control who is allowed to make changes to the product entries. | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 10
Story(product-management) As the business owner, I want only registered users to be able to create and edit products so that my site is not vandalised. | 1 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 8
Story(product-management) As the admin I want products to be linked to the user who created or last edited the product entry so that there is an audit trail. | 1 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 8
Story(product-management) As a site owner, I want to display the Brand, Title, Description, Picture, Product-type, Price of products. | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 8
Story(product-management) As a site user, I want to be able to search products based on title, description, product type so that I can quickly find the information I need | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 6
Story(product-management) As a site user, I want to be able to sort products alphabetically based on title and price so that finding what I want is easier | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 6
Story(product-management) As a site user, I want to be able to sort products alphabetically based on Brand, Product-type, Title, Price. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 1 | 1 | 6
Story(product-management) As the site owner, when a user modifies a product I want the product user property be updated to the user who made the changes so that I can track who modified it. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 8
Story(product-management) As a site owner, I do not want products that are created and linked to former employees (users who have been removed account access) to be removed from the site when their accounts are removed from the system/database. | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 1 | 8
Total Effort | 60
Actual Effort | 68
Effort Remaining | -8
Sprint 5
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Story(website): There should be an about page providing basic company details, services provided and type of products sold so that users can learn about the company and gain a better understanding of the products and services | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 10
Story(website): There should be a contact page so that users can inquire on products and services. | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 10
Story(website): There should be a page displaying products and services clearly so that users can easily discern what the company main business is about | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 10
Story(website): there should be a interface for admins so they are able to manage users (eg. delete user) | 0 | 0 | 1 | 2 | 3 | 3 | 1 | 1 | 0 | 0 | 10
Backend hosting (Heroku) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5
Frontend hosting (Netlify) | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 5
Create Final Report | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 2 | 10
Create Final Presentation Powerpoint Slides | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 5
Total Effort | 65
Actual Effort | 65
Effort Remaining | 0
Sprint 6
PBI | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Fixing Bugs | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 10
Testing App | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 10
Finalizing Final Report | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 6
Finalizing Powerpoint Slides | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 6
Presentation Practice | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 8
Documentation | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 8
Solution Presentation Preparation | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 8
Solution Presentation | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 4
Total Effort | 60
Actual Effort | 55
Effort Remaining | 5

## Gantt
[5 empty] | August 2 - 8 ,2021 | [6 empty] | August 9 - 15 ,2021 | [6 empty] | August 16 - 22 ,2021 | [6 empty] | August 23 - 29 ,2021 | [6 empty] | August 30 - September 5 ,2021 | [6 empty] | September 6 - 12 ,2021 | [6 empty] | September 13 - 19 ,2021 | [6 empty] | September 20- 26 ,2021 | [6 empty] | September 27 - October 3 ,2021 | [6 empty] | October 4 - 10 ,2021 | [6 empty] | October 11 - 17 ,2021 | [6 empty] | October 18 - 24 ,2021
[5 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
N/O | Task | Progress | Start | End | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Week 1 & 2
Project Conception and Initiation
1 | Discussion on Problem Statement and Objectives | 100% | 2021-08-02 | 2021-08-03 | bar: August 2 - 8 ,2021 2 M to August 2 - 8 ,2021 3 T
2 | Research on project topics | 100% | 2021-08-02 | 2021-08-10 | bar: August 2 - 8 ,2021 2 M to August 2 - 8 ,2021 6 F; August 9 - 15 ,2021 9 M to August 9 - 15 ,2021 10 T
3 | Discussions on project topics | 100% | 2021-08-05 | 2021-08-12 | bar: August 2 - 8 ,2021 5 T to August 2 - 8 ,2021 6 F; August 9 - 15 ,2021 9 M to August 9 - 15 ,2021 12 T
4 | Create Solution Design Presentation | 100% | 2021-08-11 | 2021-08-15 | bar: August 9 - 15 ,2021 10 T to August 9 - 15 ,2021 13 F
Week 3 & 4
1 | App Design
1.1 | Create & Finalise Database Design | 100% | 2021-08-16 | 2021-08-19 | bar: August 16 - 22 ,2021 16 M to August 16 - 22 ,2021 19 T
1.2 | Create & Finalise Api Design | 100% | 2021-08-16 | 2021-08-19 | bar: August 16 - 22 ,2021 16 M to August 16 - 22 ,2021 19 T
1.3 | Create & Finalise Wireframes Design | 100% | 2021-08-16 | 2021-08-19 | bar: August 16 - 22 ,2021 16 M to August 16 - 22 ,2021 19 T
1.4 | HTML CSS Design | 100% | 2021-08-18 | 2021-08-24 | bar: August 16 - 22 ,2021 18 W to August 16 - 22 ,2021 20 F; August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 24 T
2 | Documentation
2.1 | Documentation & Scrum | 100% | 2021-08-19 | 2021-08-25 | bar: August 16 - 22 ,2021 19 T to August 16 - 22 ,2021 20 F; August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 25 W
2.2 | Gantt Chart | 100% | 2021-08-19 | 2021-08-25 | bar: August 16 - 22 ,2021 19 T to August 16 - 22 ,2021 20 F; August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 25 W
2.3 | Burndown Chart | 100% | 2021-08-19 | 2021-08-25 | bar: August 16 - 22 ,2021 19 T to August 16 - 22 ,2021 20 F; August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 25 W
2.4 | Minutes | 100% | 2021-08-19 | 2021-08-25 | bar: August 16 - 22 ,2021 19 T to August 16 - 22 ,2021 20 F; August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 25 W
2.5 | Finalise Solution Design Presentation | 100% | 2021-08-20 | 2021-08-27 | bar: August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 27 F
2.6 | Finalise Initial Report | 100% | 2021-08-20 | 2021-08-27 | bar: August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 27 F
2.7 | Powerpoint Slides | 100% | 2021-08-20 | 2021-08-27 | bar: August 23 - 29 ,2021 23 M to August 23 - 29 ,2021 27 F
Week 5 & 6
1 | Solution Design Presentation
1.1 | Solution Design Presentation | 100% | 2021-08-30 | 2021-09-01 | bar: August 30 - September 5 ,2021 30 M to August 30 - September 5 ,2021 1 W
2 | Database Development
2.1 | Set up MongoDB. | 100% | 2021-09-01 | 2021-09-07 | bar: August 30 - September 5 ,2021 1 W to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 7 T
2.2 | Define the product schema. | 100% | 2021-09-01 | 2021-09-07 | bar: August 30 - September 5 ,2021 1 W to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 7 T
2.3 | Define user schema. | 100% | 2021-09-01 | 2021-09-07 | bar: August 30 - September 5 ,2021 1 W to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 7 T
2.4 | Define product-type schema. | 100% | 2021-09-01 | 2021-09-07 | bar: August 30 - September 5 ,2021 1 W to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 7 T
2.5 | Set up form validation for the data collection schemas. | 100% | 2021-09-01 | 2021-09-07 | bar: August 30 - September 5 ,2021 1 W to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 7 T
3 | App Development - User Management
3.1 | Set up account creation. | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.2 | Create User role. | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.2.1 | create, view and edit products | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.2.2 | edit only their own products so that unauthorised edits are not made. | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.3 | Create Admin User role. | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.3.1 | Able to create, view and edit products | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.3.2 | Able to view and edit, delete other user products | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.3.3 | Able to edit and delete users | 100% | 2021-09-02 | 2021-09-09 | bar: August 30 - September 5 ,2021 2 T to August 30 - September 5 ,2021 3 F; September 6 - 12 ,2021 6 M to September 6 - 12 ,2021 9 T
3.4 | Set up restrictions for unauthorized viewers. | 100% | 2021-09-08 | 2021-09-10 | bar: September 6 - 12 ,2021 8 W to September 6 - 12 ,2021 10 F
3.4.1 | users who are not logged in to only be able to view product cards and not edit them | 100% | 2021-09-08 | 2021-09-10 | bar: September 6 - 12 ,2021 8 W to September 6 - 12 ,2021 10 F
3.5 | Set up public view for view products page, about page, home page and contact page. | 100% | 2021-09-08 | 2021-09-10 | bar: September 6 - 12 ,2021 8 W to September 6 - 12 ,2021 10 F
4 | Documentation
4.1 | Minutes | 100% | 2021-09-08 | 2021-09-10 | bar: September 6 - 12 ,2021 8 W to September 6 - 12 ,2021 10 F
Week 7 & 8
1 | App Development - User Management
1.1 | Set up Sign up key for secure account registration. | 100% | 2021-09-13 | 2021-09-17 | bar: September 13 - 19 ,2021 13 M to September 13 - 19 ,2021 17 F
1.1.1 | Control who is allowed to make changes to the product entries. | 100% | 2021-09-13 | 2021-09-17 | bar: September 13 - 19 ,2021 13 M to September 13 - 19 ,2021 17 F
1.1.2 | Set the key as an environment variable on the server | 100% | 2021-09-13 | 2021-09-17 | bar: September 13 - 19 ,2021 13 M to September 13 - 19 ,2021 17 F
2 | App Development - Product Management
2.1 | Create product service catalogue page. | 100% | 2021-09-15 | 2021-09-21 | bar: September 13 - 19 ,2021 15 W to September 13 - 19 ,2021 17 F; September 20- 26 ,2021 20 M to September 20- 26 ,2021 21 T
2.1.1 | Includes Brand, Title, Description, Picture, Product-type, Price of all products by default. | 100% | 2021-09-15 | 2021-09-21 | bar: September 13 - 19 ,2021 15 W to September 13 - 19 ,2021 17 F; September 20- 26 ,2021 20 M to September 20- 26 ,2021 21 T
2.2 | Create product card item. | 100% | 2021-09-15 | 2021-09-21 | bar: September 13 - 19 ,2021 15 W to September 13 - 19 ,2021 17 F; September 20- 26 ,2021 20 M to September 20- 26 ,2021 21 T
2.2.1 | Displays Brand, Title, Description, Picture, Product-type, Price of one product. | 100% | 2021-09-15 | 2021-09-21 | bar: September 13 - 19 ,2021 15 W to September 13 - 19 ,2021 17 F; September 20- 26 ,2021 20 M to September 20- 26 ,2021 21 T
2.3 | Create product/service search bar and filters based on Brand, Product-type, Title, Price and alphabetically. | 100% | 2021-09-20 | 2021-09-24 | bar: September 20- 26 ,2021 20 M to September 20- 26 ,2021 24 F
2.4 | Set USER foreign key for products to be updated to link products to the user who modified it. | 100% | 2021-09-20 | 2021-09-24 | bar: September 20- 26 ,2021 20 M to September 20- 26 ,2021 24 F
2.5 | Set up USER foreign key for products to link products to their creators. | 100% | 2021-09-20 | 2021-09-24 | bar: September 20- 26 ,2021 20 M to September 20- 26 ,2021 24 F
2.6 | Ensure products that are no longer linked to users continue to exist. | 100% | 2021-09-20 | 2021-09-24 | bar: September 20- 26 ,2021 20 M to September 20- 26 ,2021 24 F
3 | Documentation
3.1 | Minutes | 100% | 2021-09-22 | 2021-09-24 | bar: September 20- 26 ,2021 22 W to September 20- 26 ,2021 24 F
Week 9 & 10
1 | App Development - Website
1.1 | Create About Page | 100% | 2021-09-27 | 2021-10-01 | bar: September 27 - October 3 ,2021 27 M to September 27 - October 3 ,2021 1 F
1.1.1 | Relevant details about company | 100% | 2021-09-27 | 2021-10-01 | bar: September 27 - October 3 ,2021 27 M to September 27 - October 3 ,2021 1 F
1.2 | Create Contact Page | 100% | 2021-09-27 | 2021-10-01 | bar: September 27 - October 3 ,2021 27 M to September 27 - October 3 ,2021 1 F
1.2.1 | Relevant contact details | 100% | 2021-09-27 | 2021-10-01 | bar: September 27 - October 3 ,2021 27 M to September 27 - October 3 ,2021 1 F
1.3 | Create Admin Page | 100% | 2021-09-29 | 2021-10-06 | bar: September 27 - October 3 ,2021 29 W to September 27 - October 3 ,2021 1 F; October 4 - 10 ,2021 4 M to October 4 - 10 ,2021 6 W
1.3.1 | only viewable with admin role account | 100% | 2021-09-29 | 2021-10-06 | bar: September 27 - October 3 ,2021 29 W to September 27 - October 3 ,2021 1 F; October 4 - 10 ,2021 4 M to October 4 - 10 ,2021 6 W
1.3.2 | view and delete users | 100% | 2021-09-29 | 2021-10-06 | bar: September 27 - October 3 ,2021 29 W to September 27 - October 3 ,2021 1 F; October 4 - 10 ,2021 4 M to October 4 - 10 ,2021 6 W
1.4 | HTML CSS Integration | 100% | 2021-09-29 | 2021-10-06 | bar: September 27 - October 3 ,2021 29 W to September 27 - October 3 ,2021 1 F; October 4 - 10 ,2021 4 M to October 4 - 10 ,2021 6 W
1.5 | Backend hosting (Heroku) | 100% | 2021-10-05 | 2021-10-08 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 7 T
1.5.1 | Push to Heroku | 100% | 2021-10-05 | 2021-10-08 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 7 T
1.6 | Frontend hosting (Netlify) | 100% | 2021-10-05 | 2021-10-08 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 7 T
1.6.1 | Push to Netlify | 100% | 2021-10-05 | 2021-10-08 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 7 T
2 | Documentation
2.1 | Create Final Report | 100% | 2021-10-05 | 2021-10-09 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 8 F
2.2 | Create Final Presentation Powerpoint Slides | 100% | 2021-10-05 | 2021-10-09 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 8 F
2.3 | Minutes | 100% | 2021-10-05 | 2021-10-09 | bar: October 4 - 10 ,2021 5 T to October 4 - 10 ,2021 8 F
Week 11 & 12
1 | App Development - Website
1.1 | Fixing Bugs | 100% | 2021-10-11 | 2021-10-15 | bar: October 11 - 17 ,2021 11 M to October 11 - 17 ,2021 15 F
1.2 | Testing App | 100% | 2021-10-11 | 2021-10-15 | bar: October 11 - 17 ,2021 11 M to October 11 - 17 ,2021 15 F
2 | Documentation
2.1 | Finalizing Final Report | 100% | 2021-10-12 | 2021-10-15 | bar: October 11 - 17 ,2021 12 T to October 11 - 17 ,2021 15 F
2.2 | Finalizing Powerpoint Slides | 100% | 2021-10-12 | 2021-10-15 | bar: October 11 - 17 ,2021 12 T to October 11 - 17 ,2021 15 F
2.3 | Presentation Practice | 100% | 2021-10-12 | 2021-10-15 | bar: October 11 - 17 ,2021 12 T to October 11 - 17 ,2021 15 F
2.4 | Documentation | 100% | 2021-10-12 | 2021-10-15 | bar: October 11 - 17 ,2021 12 T to October 11 - 17 ,2021 15 F
2.5 | Solution Presentation Preparation | 100% | 2021-10-12 | 2021-10-15 | bar: October 11 - 17 ,2021 12 T to October 11 - 17 ,2021 15 F
2.6 | Solution Presentation | 100% | 2021-10-14 | 2021-10-15 | bar: October 11 - 17 ,2021 14 T to October 11 - 17 ,2021 15 F

## Burndown
Week 11
Setting | Start | Week 1&2 | Week 3&4 | Week 5&6 | Week 7&8 | Week 9&10 | Week 11&12
Planned Hours |  | 40 | 52 | 73 | 60 | 65 | 60
Actual Hours |  | 56 | 71 | 60 | 60 | 60 | 60
Ideal Burndown | 350 | 310 | 258 | 185 | 125 | 60 | 0
Remaining Effort | 350 | 294 | 223 | 163 | 103 | 43 | -17
Week 4
Setting | Start | Week 1&2 | Week 3&4 | Week 5&6 | Week 7&8 | Week 9&10 | Week 11&12
Planned Hours |  | 40 | 52 | 73 | 60 | 65 | 60
Actual Hours |  | 56 | 71 | 83 | 68 | 65 | 55
Ideal Burndown | 350 | 310 | 258 | 185 | 125 | 60 | 0
Remaining Effort | 350 | 294 | 223 | 140 | 72 | 7 | -48

## Project Schedule
Activities | Duration (hours)
1. Requirement Analysis & Research | 30
2. Solution Design & Functional Specifications | 42
4. Project & Web App Development | 178
5. Integration and Cloud Hosting | 30
6. Project Documentation | 58
7. Demo setup | 8
8. Final Demo | 4
Total | 350